FCI CONSTRUCTORS, INC.

WEST PARK ELEMENTARY

FCI CONSTRUCTORS, INC.

WEST PARK ELEMENTARY

WEST PARK ELEMENTARY

SUPERINTENDENT WEEKLY ACTIVITY REPORT

Report Number 3

Week of 6/6/20 - 6/12	/20

Superintendent: Larry Yeager

Author: Jarred Collom

CURRENT CONSTRUCTION ACTIVITIES

Enabling Site Work

- Over Lot Grading cut/fill

- Pad and Footing Excavation

- Underground Utility Install

- Pour slab for Water Fill Station

- Begin Footing Formwork

CONSTRUCTION ACTIVITIES IMAGES

MANPOWER COUNT

| Trade Partners | Responsibility | Manpower Count |
| --- | --- | --- |
| FCI Constructors, Inc. | General Contractor | 3 |
| Schofield | Site Capture/Earthwork/Utilities | 8 |
| RMS Concrete | Forming | 10 |
|  | Total: | 21 |

WEATHER CONDITIONS

- Weather days this week: 0

- Weather days to date: 0

UPCOMING WEATHER RISKS

- Currently, no weather risks are forecasted.

SAFETY REPORT

- Lost Time Accidents to Date = 0

- Accidents This Week = 0

- Days Without Lost Time = 36

INSPECTIONS/TESTING REPORT

- All inspection parties present for their responsibilities

  - Soil Compaction Testing (Ground Engineering) - ongoing

NEXT WEEK’S ACTIVITIES

Site Work

- Pad and Footing Excavation

- Underground Utility Install

- Begin Sanitary Sewer Installation

- Prep Footings for Existing Play Area

- Prep Footings for New ECE

- Water Fill Station Relocation

- Water Line Tap

- Form and Pour Footings