

**FCI CONSTRUCTORS, INC.**

WEST PARK ELEMENTARY

**WEST PARK ELEMENTARY**

**SUPERINTENDENT WEEKLY ACTIVITY REPORT**

Report Number 3

Week of 6/6/20 - 6/12 /20

*Superintendent: Larry Yeager*

*Author: Jarred Collom*

****

**CURRENT CONSTRUCTION ACTIVITIES**

Enabling Site Work



* Over Lot Grading cut/fill
* Pad and Footing Excavation
* Underground Utility Install
* Pour slab for Water Fill Station
* Begin Footing Formwork

**CONSTRUCTION ACTIVITIES IMAGES**

**MANPOWER COUNT**

|  |  |  |
| --- | --- | --- |
| Trade Partners | Responsibility | Manpower Count |
| FCI Constructors, Inc. | General Contractor | 3 |
| Schofield | Site Capture/Earthwork/Utilities | 8 |
| RMS Concrete | Forming | 10 |
|  | **Total:** | **21** |

**WEATHER CONDITIONS**

****

* Weather days this week: **0**
* Weather days to date: **0**

**UPCOMING WEATHER RISKS**

* Currently, no weather risks are forecasted.

**SAFETY REPORT**

* Lost Time Accidents to Date = **0**
* Accidents This Week = **0**
* Days Without Lost Time = **36**

**INSPECTIONS/TESTING REPORT**

* All inspection parties present for their responsibilities
  + Soil Compaction Testing (Ground Engineering) - **ongoing**

**NEXT WEEK’S ACTIVITIES**

Site Work

* Pad and Footing Excavation
* Underground Utility Install
* Begin Sanitary Sewer Installation
* Prep Footings for Existing Play Area
* Prep Footings for New ECE
* Water Fill Station Relocation
* Water Line Tap
* Form and Pour Footings